## Sheet1
Architecture Risk Analysis - Data Sheet
Solution Overview | Solution Name | FibroScan (Echosens Expert 630) Epic Integration via Gateway Server
| Vendor | Echosens
| Scope (Site/Regional/Enterprise) | Site — AH Porter / Rocky Mountain Region
| Architecture Model (Centralized/Distributed) | Distributed on-premises integration: Epic + Mirth Connect + Gateway VM + local MongoDB + FibroScan device
| Reviewer | Architecture / Technical Risk Assessment
| Date | 2026-09-02
Section | Check | Status (Pass/Gap/Risk) | Risk Level (Low/Med/High) | Notes | Mitigation Controls | Owner | Remediation Timeline
IAM | Supports multi-domain AD | Risk | High | Current Gateway version does not integrate with AdventHealth enterprise authentication. Separate local accounts are required; the vendor roadmap targets LDAP/AD integration for Q1 2028. | Document the policy exception, local-account ownership, least privilege, joiner/mover/leaver procedures, and roadmap tracking. | IAM / Security Governance + Application Support | Before go-live; Q1 2028 roadmap review; ongoing
| Supports SSO (SAML/OIDC) | Risk | High | The technology assessment identifies no enterprise authentication or MFA support, creating a CW IS SEC 110 policy violation. Users must use separate Gateway credentials. | Obtain and document the governance policy exception; restrict access to authorized administrators; enforce strong unique credentials and approved credential storage. | Security Governance + Product Owner | Before go-live
| LDAP/AD roadmap timing | Risk | Med | LDAP/AD integration is not available in the current version; Echosens lists it on the product roadmap for Q1 2028. | Track the vendor roadmap, reassess enterprise authentication/MFA readiness when delivered, and retain local-account controls until validated in production. | Vendor + IAM / Application Support | Q1 2028 vendor roadmap
| Local user management required | Risk | Med | Local Gateway accounts are expected because enterprise SSO is not supported in the current version. | Maintain an account inventory, review access periodically, remove inactive accounts, and store credentials in the approved enterprise vault. | Application Support | Before go-live; quarterly
| RBAC maturity | Gap | Med | RBAC maturity is not fully documented in the supplied materials. | Obtain vendor role matrix; assign least privilege and restrict administrative functions to designated support staff. | Vendor + Application Support | Before go-live
High Availability & Resiliency | Application-level HA | Gap | Med | No application-level HA or clustered deployment is identified; the design uses a small on-premises VM. | Use VM infrastructure protections, documented rebuild steps, tested backups, and downtime procedures. Confirm business availability expectations. | Infrastructure + Application Support | Before go-live
| Clustering/Active-Active | Gap | Med | Active-active or clustered Gateway deployment is not identified in vendor materials. | Treat the Gateway as a single-site service unless vendor confirms a supported HA pattern. Document single-server dependency and recovery procedure. | Infrastructure | Design confirmation
| Load balancing | Pass | Low | No load balancer is required for the proposed single-site architecture. | Keep Gateway access internal and limit management traffic to approved support networks. | Infrastructure | Before go-live
| Downtime during patching | Risk | Med | Patching or certificate updates may cause service interruption; vendor notes manual certificate updates and a self-signed TLS 1.2 certificate by default. | Schedule maintenance, validate certificate renewal, use a Microsoft-recognized CA certificate where available, and test order/result flow after changes. | Infrastructure + Vendor | Before go-live; maintenance windows
| Backup automation | Gap | Med | Backup automation is not defined in the supplied requirements. MongoDB is local to the Gateway environment. | Include Gateway configuration, MongoDB data, interface configuration, and certificates in enterprise VM/backup policy; perform restore testing. | Infrastructure | Before go-live
Database | Database type (standard vs proprietary) | Pass | Low | MongoDB is a standard supported component for Gateway v2; vendor prerequisites identify MongoDB 7.0.6–8.0.3. | Keep MongoDB local to the Gateway host or protected server segment and manage it under enterprise patch/backup standards. | Infrastructure | Before go-live; ongoing
| External DB supported | Gap | Med | External database support is not established; the vendor prerequisite describes a local MongoDB dependency. | Use the vendor-supported local deployment unless Echosens documents a supported external database architecture. | Vendor + Infrastructure | Design confirmation
| Alignment with enterprise DB strategy | Gap | Med | The local MongoDB dependency does not align with a centralized enterprise database service by default. | Document the approved exception/architecture decision and apply enterprise backup, patching, access, and encryption standards to the local database. | Infrastructure + Security Architecture | Before go-live
| Scalability | Gap | Med | Scalability limits for the single-device, single-site design are not specified. | Confirm expected study volume and concurrent device count; review capacity if additional devices or facilities are added. | Product Owner + Vendor | Before go-live
| Data growth handling | Pass | Low | Expected data volume is modest for one FibroScan device; the assessment records an estimated 1–1,000 range. | Monitor disk utilization and retain reports according to enterprise policy. | Application Support | Ongoing
Architecture Model | Supports centralized deployment | Pass | Low | Centralized deployment is supported for this use case through an on-premises Gateway VM serving the AH Porter device and Epic integration. | Keep the Gateway close to the device and Epic interface path; document the final host and network segment. | Infrastructure | Before go-live
| Latency, network authentication & segmentation | Risk | High | The solution does not support the required secure network authentication method under CW IS SEC 108. Device placement may require segmentation from the production network and a wired connection; device-to-Gateway reachability and latency must be validated. | Design an approved segmented VLAN and firewall path; validate same-subnet or otherwise unrestricted device-to-Gateway connectivity, wired requirements, and end-to-end order/result testing before go-live. | Network Engineering + Security Architecture | Before go-live
| Facility isolation requirements (CAP/CLIA) | Pass | Low | A single AH Porter facility is identified; no CAP/CLIA facility-isolation requirement is identified in the supplied demand. | Confirm whether additional facilities or laboratory-regulated workflows are added later. | Product Owner | Design confirmation
| Migration flexibility | Pass | Low | The solution is an on-premises software integration and can be rebuilt or replaced using vendor installation materials, subject to interface mapping. | Maintain installation/configuration documentation and export interface mappings. | Application Support | Before go-live; update on change
Security | HIPAA compliance controls | Risk | High | The product processes PHI and lacks enterprise SSO/MFA. The TPRM/technology review recommends proceeding only with governance acceptance and a documented policy exception for the identified policy violation(s). | Complete and approve the policy exception; limit access, enforce network restrictions, use approved certificates, and include vendor commitments in contract/support strategy. | Security Governance + Business Owner | Before go-live
| Audit logging | Pass | Low | Gateway/Mirth support logging is expected, but the supplied materials do not define centralized audit-log forwarding or retention. | Confirm available audit events and forward relevant logs to enterprise monitoring/SIEM where supported. | Security Operations | Before go-live
| Encryption in transit | Risk | Med | REST/HTTP(S), HL7, and management connections are required. The Gateway supplies a self-signed TLS 1.2 certificate by default, and the assessment identifies manual certificate remediation as an operational risk. | Use HTTPS/TLS where supported; replace the self-signed certificate with a Microsoft-recognized CA certificate; assign a renewal owner, monitor expiration, validate protocol/cipher settings, and test the order/result flow after renewal. | Network Security + Infrastructure | Before go-live
| Encryption at rest | Gap | Med | Encryption at rest is not explicitly documented for the local MongoDB/application data. | Confirm vendor support for disk/database encryption; use encrypted VM/storage volumes and restrict host access. | Security Architecture + Infrastructure | Before go-live
| Remote access controls | Pass | Low | Unmonitored vendor access is not required according to the due-diligence review. Any support access still needs to be controlled and monitored. | Permit vendor access only through approved, time-bound, monitored remote-support methods; prohibit standing unattended access and retain access records. | Application Support + Security Operations | Before go-live; per incident
Operations | Monitoring centralized | Gap | Med | Centralized monitoring requirements are not defined in the vendor package. | Monitor VM health, disk space, Windows services, Mirth channels, MongoDB, Gateway availability, and interface failures. | Infrastructure + Application Support | Before go-live
| Patch management defined | Gap | Med | Patch ownership and cadence are not fully defined across Windows, Mirth, MongoDB, Gateway, and device software. | Assign patch owners, use change control, review vendor compatibility, and test the end-to-end workflow after patching. | Infrastructure + Vendor | Before go-live; monthly/quarterly
| Vendor dependency | Risk | Med | The workflow depends on Echosens Gateway software, vendor support, and FibroScan device compatibility. | Add vendor obligations, supported-version commitments, escalation contacts, and response targets to the support strategy/contract. | Business Owner + Procurement | Before go-live
| Automation support | Gap | Med | Automation is provided through HL7 ORM/ORU and REST/API exchanges, but operational automation for monitoring, backup, and certificate renewal is not defined. | Automate health checks and backup verification where possible; document manual fallbacks. | Application Support + Infrastructure | Before go-live
Disaster Recovery | RPO defined | TBD | Med | Formal RPO is not defined in the demand or prerequisite documents. | Set RPO with the business owner; recommended starting point is aligned to enterprise VM/database backup policy. | Business Owner + Infrastructure | Before go-live
| RTO defined | TBD | Med | Formal RTO is not defined in the demand or prerequisite documents. | Set RTO with the business owner and document the rebuild/restore procedure for the Gateway VM and interfaces. | Business Owner + Infrastructure | Before go-live
| DR automation | Gap | Med | Automated DR orchestration is not identified for this single-site Gateway deployment. | Use enterprise backup/restore and VM recovery capabilities; test recovery and document manual steps. | Infrastructure | Before go-live; annual test
| Failover capability | Gap | Med | No application failover capability is identified; availability depends on the Gateway VM and local device/network path. | Document the single-server dependency, maintain tested backups and a recovery VM/build process, and define downtime/manual-result procedures. | Infrastructure + Application Support | Before go-live